## Sheet1
Date | Work Content
28/02/2017 | 1.Meet supervisor 2.learn Scrum
01/03/2017 | 1.learn Scrum
02/03/2017 | 1.prepare questions to ask the clients 2.weekly project meeting 3.begin revise the project proposal
04/03/2017 | 1.look for some article about HRMS
05/03/2017 | 1.revise project proposal 2.add questions
06/03/2017 | project proposal
07/03/2017 | meet the client first time and talk about their requirements
08/03/2017 | photocopy the materials of the requirements got from the client Nicole.
09/03/2017 | sort out the materials
10/03/2017 | write project prososal
11/03/2017 | write project prososal
12/03/2017 | finish and submit the project proposal
13/03/2017 | Meet the client in her office talking about the technical requirement with IT staff and business requirements with Nicole
14/03/2017 | Project meeting in Room E202 with Sunil and team mates
15/03/2017 | Write some questins about the requirement and send them to Nicole
16/03/2017 | Meet Nicole in Room E202 and discuss the questions of the requirements
17/03/2017 | Write the requirement documents(requirement list)
20/03/2017 | Write the requirement documents(requirement list)
21/03/2017 | 1.Have an online meeting with Sunil and team mates; 2.Finish writing the requirement list
22/03/2017 | Write requirement specification
23/03/2017 | Write requirement specification
24/03/2017 | Write requirement specification
27/03/2017 | Discuss the requirement documents with the client,
28/03/2017 | Project meeting in Room E202 with Sunil and team mates, Sunil gave us some advice about the project proposal
29/03/2017 | prepare for the progress review report1
30/03/2017 | progress review report1
31/03/2017 | revise the project proposal and requirement documents
03/04/2017 | revise the project proposal and requirement documents
04/04/2017 | Sent the client the proposal and requirement documents of final version
05/04/2017-12/04/2017 | DB design - conceptual model,logical model and physical model
11/04/2017 | Projet meeting onling
12/04/2017-14/04/2017 | UI design: login, master page, create employee, maintain employee and query employee
17/04/2017-21/04/2017 | Establish the environment of devlopment and devloped the function of login(prototype)
24/04/2017-28/04/2017 | Finish developing the function of crate,modify and query of employee information (prototype)
30/04/2017 | implement the function of exporting the data as Excel file
01/05/2017 | 1.Change definition of table StaffSize and Attendance 2.UI design 3.Study Git
02/05/2017 | 1. Modify functions of login,add employee, modify employee and query employee. 2.Develop the funcitons of Attendance(New and Query)
03/05/2017 | Develop the functions of Vehicle(New and Query)
04/05/2017 | 1.Develop the function of ChangePassword 2.Develop the function of ToolTraining 3.Project progress report
05/05/2017 | 1.Develop the function of TimeSheet 2.Develop the function of Wage 3.Develop the function of EmployeeHistory
06/05/2017 | 1.Develop the function of Competency 2.Update the function of Employee Maintain 3.Develop the function of Tax report
07/05/2017 | 1.Finishing devloping the function of Competency 2.Modify the definition of table Employee and relative codes
08/05/2017 | 1.Improve the function of Competency: Can export PDF file 2.Imporeve the function of Login:Can update YearsInIndustry automatically 3.Develop the function of Certification
09/05/2017 | 1.Finishing devloping the function of Certification 2.Projec team meeting 3.Confirm database struture
10/05/2017 | 1.Help team mates with their problems 2.Implement session control
11/05/2017 | 1.Develop the function of ToolUse 2.Develop the function of ToolList 3.Develop the function of StaffSize
12/05/2017 | Test 7 functions
13/05/2017 | 1.Test 10 functions 2.Update function of Certification 3.Add format validation of Email and Date
14/05/2017 | 1.Finish testing 2.Develop the function of StaffCouse 3.Add format validation of Email and Date
15/05/2017 | 1.Deployment test 2.Revise ERD diagram
16/05/2017 | 1.Project team meeting 2.Meet client, begin user's test 3.Prepare the system intallation documents and files
17/05/2017 | 1.Deploy the system in clients office
18/05/2017 | Write test record templet
19/05/2017 | Write database automatic backup scripts
20/05/2017 | Write user manul
21/05/2017 | Write database automatic backup scripts
22/05/2017 | 1.Project team meeting 2.Write system documents
23/05/2017 | Fix bugs
24/05/2017 | Take part in the training of Poster and Presentation
25/05/2017 | 1.Meet client, and the client promote some new requirement 2.Sort throuth the new requirement
26/05/2017 | Write system document
27/05/2017 | Write system document
28/05/2017 | Write system document
29/05/2017 | Write project final status report
30/05/2017 | Project meeting:discuss the new requirements of the system
31/05/2017 | Deploy the system in production environment
01/06/2017 | Project progress report 3
02/06/2017 | Project work end