## Sheet1
Date | Time | Room | Attendees | Content
3/3/2017 | 10:00 | E202 | Tao Sun Damian Tait Konark Bhurke | Discuss what to talk with supervisor tomorrow; Everybody think over the questions to ask the client
8/3/2017 | 9:55 | E202 | Tao Sun Damian Tait Konark Bhurke | Met before client meeting Went over questions and eliminated duplicate questions
10/3/2017 | 13:55 | E204 | Tao Sun Damian Tait | Briefly spoke about emailing client meeting minutes and that Damian would proofread the proposal when finished
13/3/2017 | 9:30 | E202 | Tao Sun Damian Tait Konark Bhurke | Spoke briefly about what we would discuss with the client at their workplace Spoke after meeting with client as to our next steps
15/3/2017 | 13:55 | E204 | Tao Sun Damian Tait | Spoke on break in class about progress.
27/3/2017 | 9:55 | E202 | Tao Sun Konark Bhurke Damian Tait | Spoke about what we were going to discuss with the client. Tao showed the early stage of an ERD and spoke of the requirements document
28/3/2017 | 9:55 | E202 | Tao Sun Konark Bhurke Damian Tait | Discussed what we would speak about at the first oral presentation in front of Project Management class, went over subject matter, continued research on client requests.
30/3/2017 | 12:55 | E202 | Tao Sun Konark Bhurke Damian Tait | Discussed further progress and future concepts
4/4/2017 | 9:55 | E202 | Tao Sun Damian Tait Konark Bhurke | Spoke of switching to Visual Paradigm for Conceptual and Logical Models Discussed finishing planning stages
5/4/2017 | 9:55 | E202 | Tao Sun Konark Bhurke Damian Tait | Emailed all outstanding documents to client and so on and so forth
10/4/2017 | 9:55 | E202 | Tao Sun Konark Bhurke Damian Tait | Discussed a meeting with the client on the first Monday back after study break
12/4/2017 | 11:48 | E202 | Tao Sun Konark Bhurke Damian Tait | Tao sent an email contained all logical and conceptual diagrams as well as database coding to other group members.
1/5/2017 | 11:55 | E202 | Tao Sun Konark Bhurke Damian Tait | Discuss what we have done in the study break, Allocate jobs to do from this point on Discuss Second Oral Presentation
2/5/2017 | 9:55 | E202 | Konark Bhurke Damian Tait Tao Sun | Discuss progress on jobs Try to get more work done Go home to try and sort out problems
4/5/2017 | 12:55 | E202 | Konark Bhurke Damian Tait Tao Sun | Discuss second presentation and talk more about progress on front-end application
5/5/2017 | 10:55 | N/A | Tao Sun Damian Tait | Sent meeting minutes to Sunil for review
2017-05-09 | 9:55 | E202 | Konark Bhurke Damian Tait Tao Sun | Discuss weekend progress
2017-05-10 | 13:10 | E204 | Konark Bhurke Damian Tait Tao Sun | Reallocate tasks due to Damian's inexperience with ASP.net
2017-05-16 | 9:55 | E202 | Konark Bhurke Damian Tait Tao Sun | Discuss progress on deliverables so far. Have a look over completed program and database.
2017-05-17 | 9:25 | E202 | Konark Bhurke Damian Tait Tao Sun | Discuss system installation at BCD Carpentry. Discuss further actions at this point.
2017-05-25 | 9:55 | E202 | Konark Bhurke Damian Tait Tao Sun | Discuss upcoming presentations and progress. Consider changes requested by client and whether they're feasible at this point.
2017-05-28 | 16:30 | N/A | Konark Bhurke Damian Tait Tao Sun | Tao asked us other two to work on poster-related deliverables.
2017-05-30 | 9:55 | E202 | Konark Bhurke Damian Tait Tao Sun | Discuss what has been changed and what hasn't in program. Discuss future actions regarding presentation and poster creation.
2017-06-01 | 9:25 | E202 | Konark Bhurke Damian Tait Tao Sun | Discuss installing final copy of the system on client's computer and oral presentation taking place that afternoon.