## Sheet1
Date/Time | 2017-02-28 09:45
Present | Sunil, Konark, Damian, Tao
Absent | -
Room | E202
Points | 1. Setup project proposal document and project min/attendance document in google docs for ease of collabration
2. Discuss project proposal document.
3. Distribution of duties per member (who is going to do what....?)
4. Decide methodology
5. Decide on technology.
Date/Time | 2017-03-07 14:00
Present | Nicole,Sunil, Konark, Damian, Tao
Absent | -
Room | E202
Points | 1. Work throgh the question list.
2. Nicole introduced her routine work content.
3. Nicole showed the docs and sheets she uses in work and explained how they are used.
4. Nicole introduced her thought about the new system.
5. Decide when and where we will meet next time.
6. Sunil told team member what they should pay attention to next in the project.
Date/Time | 2017-03-13 11:00
Present | Nicole,Konark, Damian, Tao
Absent | -
Room | Nicole's office
Points | 1. Talk with the IT man of BCD about their technology requirments
Date/Time | 2017-03-14 10:00
Present | Sunil, Konark, Damian, Tao
Absent | -
Room | E202
Points | 1.Talk about the project team's meeting with Nicole in her office on this Monday.
2. Sunil taught the team some thinking about how to design database table
Date/Time | 2017-03-16 10:00
Present | Niclole, Tao, Damian, Konark
Absent | -
Room | E202
Points | 1.Worked through the questions about the requirements.
2. NIcole signed the agreement.
3. Planed to finish the requirement documents next week.
Date/Time | 2017-03-21 10:00
Present | Sunil, Tao, Damian, Konark
Absent | -
Room | Meeting online
Points | 1.Discussed the problems with the project by now.
2. Sunil asked the progress of the project and the agreement document.
3. Planed the work of this week (write requirment document) and work of next step(DB design).
4. Reminded the presentation of next week
Date/Time | 2017-03-27 10:00
Present | Niclole, Tao, Damian, Konark
Absent | -
Room | E202
Points | 1.Confire the requirements specification
2.Discuss the presentation this Thursday.
Date/Time | 2017-03-28 10:00
Present | Sunil, Tao, Damian, Konark
Absent | -
Room | E202
Points | 1.Sunil gave us advices on how to revise the project prosoal
Date/Time | 2017-04-04 10:00
Present | Niclole, Tao, Damian, Konark
Absent | -
Room | E202
Points | 1. Project goes well
Date/Time | 2017-04-11 10:00
Present | Sunil, Tao, Damian, Konark
Absent | -
Room | Metting online
Points | 1.Sunil introduce a book on project management
2. Make clear of each team member's role in the project
3. Decide the time we meet the client
Date/Time | 2017-05-01 12:00
Present | Niclole, Tao, Damian, Konark
Absent | -
Room | E202
Points | 1. Demonstrate the prototype 2. Confirm some requirment questions
Date/Time | 2017-05-02 10:00
Present | Sunil, Tao, Damian, Konark
Absent | -
Room | E202
Points | Talk about that there is no enough time for our remaining work
Date/Time | 2017-05-09 10:00
Present | Sunil, Tao, Damian, Konark
Absent | -
Room | E202
Points | 1.Introduce the project's progress and probloms 2.Team members planed to meet the next day to talk about some technique problems
Date/Time | 2017-05-16 10:00
Present | Sunil, Tao, Damian, Konark
Absent | -
Room | E202
Points | 1. Project team have finish the development
2. Plan the test
Date/Time | 2017-05-23 10:00
Present | Sunil, Tao, Damian, Konark
Absent | -
Room | E202
Points | Discide when we will meet the client to get the test feedback
Date/Time | 2017-05-30 10:00
Present | Sunil, Tao, Damian, Konark
Absent | -
Room | E202
Points | 1. Sunil introduce the contents and process of project assessment
2. Sunil introduce how to write poster